## Worksheet
Task ID | Task Name | Due Date | Priority | Status | Budget (USD) | Actual Cost (USD) | Progress %
T-001 | Project Kickoff Meeting | 2024-04-05 | High | On Track | 500 | 480 | 96%
T-002 | Market Research Phase | 2024-04-15 | Medium | In Progress | 2,000 | 1,850 | 92.5%
T-003 | Development Sprint 1 | 2024-05-10 | High | On Track | 8,000 | 7,450 | 93.1%
T-004 | Client Review & Feedback | 2024-06-05 | Low | Pending | 1,200 | 0 | 0%