## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Budget (USD) | Actual Cost (USD) | Progress (%) | Priority
TSK-001 | Project Planning & Kickoff | Jane Doe | 2024-03-15 | 2024-03-25 | On Track | 15,000 | 12,800 | 92% | High
TSK-002 | Market Research Phase | John Smith | 2024-03-26 | 2024-04-10 | In Progress | 8,500 | 5,200 | 67% | Medium
TSK-003 | UI/UX Design Finalization | Sarah Lee | 2024-04-11 | 2024-05-05 | Planned | 12,000 | 0 | 0% | High
TSK-004 | Development Phase (Phase 1) | Mike Chen | 2024-05-06 | 2024-06-15 | Pending Approval | 35,000 | 18,700 | 42% | Critical
TSK-005 | QA & Testing Cycle | Lisa Wong | 2024-06-16 | 2024-07-10 | On Track | 10,000 | 9,450 | 95% | Medium
Total Tasks |  |  |  | 5 | Total Budget (USD) |  |  | 80,500