## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Budget (USD) | Actual Cost (USD) | Progress (%) | Priority
TSK-001 | Project Kickoff Meeting | Jane Doe | 2024-03-15 | 2024-03-15 | Completed | 500 | 480 | 100% | High
TSK-002 | Market Research Survey | John Smith | 2024-03-18 | 2024-04-15 | In Progress | 3,500.00 | 1,850.00 | 62% | Medium
TSK-003 | UI/UX Design Phase | Lisa Chen | 2024-04-01 | 2024-05-10 | Pending | 8,200.00 | - | 0% | High
TSK-004 | Development Sprint 1 | Mike Brown | 2024-05-11 | 2024-06-30 | Planned | 15,000.00 | - | 0% | Medium
TSK-005 | QA Testing & Validation | Sarah Lee | 2024-07-10 | 2024-08-15 | Completed | 6,500.00 | 6,380.00 | 100% | Low