## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | Budget (USD) | Actual Cost (USD) | Progress (%) | Priority | Dependents
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | 3 | Completed | 500 | 485.25 | 100% | High | None
TSK-002 | Market Research Phase | Mark Johnson | 2024-04-04 | 2024-04-15 | 12 | In Progress | 8,000.00 | 5,230.50 | 65% | Medium | TSK-001
TSK-003 | UI/UX Design Finalization | Sarah Lee | 2024-04-16 | 2024-05-10 | 35 | Planned | 12,500.00 | - | 0% | High | TSK-002
TSK-004 | Development Phase - Backend | David Kim | 2024-05-11 | 2024-06-30 | 60 | Not Started | 35,000.00 | - | 0% | Critical | TSK-003
TSK-005 | QA & Testing Cycle | Lisa Wong | 2024-07-01 | 2024-07-31 | 31 | Planned | 6,800.00 | - | 0% | Medium | TSK-004
Total Budget (USD) | [5 empty] | 57,800.00 | 11,215.75 | Overall Progress: 63%