## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Budget (USD) | Current Spend | Remaining Budget | Priority
TSK-001 | Website Redesign | Ana Reyes | 2024-03-15 | 2024-04-15 | In Progress | 5,000 | 2,800 | 2,200 | High
TSK-002 | Mobile App Development | David Kim | 2024-03-20 | 2024-05-10 | Planned | 15,000 | 0 | 15,000 | High
TSK-003 | Content Creation Campaign | Lena Patel | 2024-04-01 | 2024-05-31 | Pending Approval | 3,500 | 800 | 2,700 | Medium
TSK-004 | SEO Strategy Review | Marco Ruiz | 2024-03-30 | 2024-04-10 | Completed | 1,200 | 1,200 | 0 | Low
TSK-005 | User Testing Phase | Sophia Liu | 2024-04-12 | 2024-05-05 | On Hold | 4,800 | 1,500 | 3,300 | High
Total Tasks: |  |  |  | 5 | Total Budget (USD): |  |  |  | 30,500