## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Status | Budget (USD) | Actual Cost (USD) | Progress (%) | Priority
TSK-001 | Market Research Phase | 2024-03-15 | 2024-03-30 | Sarah Johnson | On Track | 5,000 | 4,800 | 96% | High
TSK-002 | Product Launch Campaign | 2024-04-05 | 2024-05-31 | Mike Chen | Delayed | 80,000 | 65,200 | 75% | High
TSK-003 | Customer Feedback Analysis | 2024-03-25 | 2024-04-15 | Linda Patel | On Track | 15,000 | 14,750 | 98% | Medium
TSK-004 | Team Training Workshop | 2024-04-18 | 2024-04-20 | David Kim | Completed | 5,500 | 5,400 | 100% | Medium
TSK-005 | Q3 Financial Review | 2024-05-10 | 2024-05-30 | Elena Rodriguez | Planned | 7,000 | 0 | 0% | Low