## Worksheet
Month | Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Budget (USD) | Actual Cost (USD) | Progress (%)
January 2024 | TSK-001 | Project kickoff meeting planning | Jane Doe | 2024-01-01 | 2024-01-15 | Completed | 500 | 480 | 100%
January 2024 | TSK-002 | Market research survey deployment | John Smith | 2024-01-10 | 2024-01-30 | In Progress | 2,500.00 | 1,850.00 | 74%
January 2024 | TSK-003 | Vendor onboarding process | Alice Brown | 2024-01-15 | 2024-01-31 | Pending | 3,200.00 | - | 0%
January 2024 | TSK-004 | Quarterly financial review | Mike Johnson | 2024-01-25 | 2024-01-30 | Scheduled | 800 | - | 0%