## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Budget (USD) | Progress (%) | Resource Allocation
TSK-001 | Project Initiation Phase | John Smith | 2024-03-01 | 2024-03-15 | On Track | 5,000.00 | 95% | Full Team (3)
TSK-002 | Market Research & Analysis | Lisa Wong | 2024-03-16 | 2024-04-10 | In Progress | 8,500.00 | 65% | Marketing Team (2)
TSK-003 | Product Design Finalization | Mike Johnson | 2024-04-11 | 2024-05-30 | Planned | 12,000.00 | 0% | Design Team (4)
TSK-004 | Development Phase Start | Sarah Lee | 2024-06-01 | 2024-08-31 | Not Started | 35,000.00 | 0% | Engineering Team (6)