## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Budget (USD) | Actual Cost (USD) | Progress (%) | Priority
TSK-001 | Project Requirements Analysis | Sarah Johnson | 2024-03-01 | 2024-03-15 | On Track | 5,000 | 4,800 | 96% | High
TSK-002 | UI/UX Design Phase | Michael Chen | 2024-03-16 | 2024-04-05 | In Progress | 8,000 | 6,200 | 77% | High
TSK-003 | Backend Development | David Kim | 2024-04-06 | 2024-05-30 | Planned | 30,000 | 0 | 0% | Critical
TSK-004 | User Testing & Feedback | Linda Patel | 2024-06-01 | 2024-06-30 | Scheduled | 7,500 | 0 | 0% | Medium
TSK-005 | Final Deployment & Launch | Team Lead | 2024-07-01 | 2024-07-31 | Not Started | 9,000 | 0 | 0% | Critical