## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Budget (USD) | Progress (%) | Responsible Team
T-001 | Project Kickoff Meeting | Marketing Team | 2024-04-01 | 2024-04-05 | On Track | Medium | 1,500.00 | 100% | Project Planning
T-002 | UI/UX Design Phase | Design Team | <>2024-04-062024-05-15 | In Progress | High | 8,000.00 | 65% | Design & UX
T-003 | Backend Development | Engineering Team | 2024-05-16 | 2024-07-30 | Planned | High | 15,000.00 | 0% | Engineering & DevOps
T-004 | QA Testing Phase | QA Team | 2024-08-01 | 2024-08-15 | On Track | Medium | 4,500.00 | 90% | Quality Assurance
T-005 | User Training & Rollout | Operations Team | 2024-08-16 | 2024-09-30 | Pending Approval | Low | 2,000.00 | 20% | Operations & Support