## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Budget (USD) | Status | Priority | Progress (%)
TS-001 | Market Research Survey | Sarah Johnson | 2024-03-15 | 2024-03-30 | 15 | 5,000 | On Track | Medium | 85%
TS-002 | Product Design Finalization | Michael Chen | 2024-03-20 | 2024-04-10 | 21 | 15,000 | In Progress | High | 60%
TS-003 | Development Phase Launch | Emily Rodriguez | 2024-04-01 | 2024-05-15 | 45 | 75,000 | Planned | High | 0%
TS-004 | QA Testing & Validation | David Kim | 2024-04-15 | 2024-05-01 | 17 | 8,500 | Not Started | Medium | 0%