## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Budget (USD) | Actual Cost (USD) | Progress (%) | Priority
TSK-001 | Market Research Survey | Jane Doe | 2024-03-15 | 2024-03-31 | On Track | 5,000.00 | 4,250.00 | 85% | Medium
TSK-002 | Product Launch Planning | John Smith | 2024-04-01 | 2024-05-15 | In Progress | 15,000.00 | 9,875.00 | 62% | High
TSK-003 | Customer Feedback Analysis | Sarah Lee | 2024-03-25 | 2024-04-15 | Completed | 3,500.00 | 3,175.00 | 95% | Low
TSK-004 | Marketing Campaign Design | Mike Chen | 2024-04-10 | 2024-05-31 | Delayed | 8,000.00 | 7,650.00 | 48% | High