## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Assigned To | Priority | Dependency | Progress (%) | Status
T001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | John Doe | High | None | 100% | Completed
T002 | Requirements Gathering | 2024-03-16 | 2024-03-31 | 16 | Jane Smith | High | T001 | 75% | In Progress
T003 | System Design Finalization | 2024-04-01 | 2024-04-15 | 15 | Mike Johnson | Medium | T002 | 30% | Not Started
T004 | Development Phase (Phase 1) | 2024-04-16 | 2024-05-31 | 46 | Team A | High | T003 | 20% | In Progress
T005 | Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | Team B | High | T004 | 0% | Not Started
T006 | Deployment & Go-Live | 2024-07-01 | 2024-07-15 | 15 | Operations Team | Critical | T005 | 0% | Not Started