## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies
T001 | Project Initiation | 2024-03-15 | 2024-03-18 | 4 | John Doe | Completed | None
T002 | Requirement Gathering | 2024-03-19 | 2024-04-05 | 17 | Jane Smith | In Progress | T001
T003 | Design Phase | 2024-04-06 | 2024-04-25 | 20 | Mike Johnson | Not Started | T002
T004 | Development | 2024-04-26 | 2024-06-15 | 61 | Sarah Lee | Not Started | T003
T005 | Testing & QA | 2024-06-16 | 2024-07-10 | 35 | David Brown | Not Started | T004
T006 | Deployment & Launch | 2024-07-11 | 2024-07-15 | 5 | Lisa Wong | Not Started | T005