## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status
T001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Jane Doe | On Track
T002 | Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | John Smith | In Progress
T003 | Design Phase | 2024-04-11 | 2024-04-25 | 15 | Lisa Brown | On Track
T004 | Development Phase | 2024-04-26 | 2024-05-31 | 36 | Mike Johnson | Planned
T005 | Testing & QA | 2024-06-01 | 2024-06-15 | 15 | Sarah Lee | Delayed
T006 | Deployment & Go-Live | 2024-06-16 | 2024-06-18 | 3 | David Wilson