## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
T001 | Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Jane Smith | Completed | High
T002 | Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | John Doe | In Progress | High
T003 | Design Phase | 2024-03-16 | 2024-04-10 | 35 | Alice Johnson | Planned | Medium
T004 | Development | 2024-04-11 | 2024-06-30 | 90 | Mike Brown | Pending | High
T005 | Testing & QA | 2024-07-01 | 2024-07-31 | 31 | Sarah Lee | Not Started | High
T006 | Deployment | 2024-08-01 | 2024-08-15 | 15 | David Wilson | Planned | Medium