## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status
T001 | Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Jane Smith | On Track
T002 | <Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Mike Johnson | In Progress
T003 | Design Phase | 2024-04-11 | 2024-05-15 | 45 | Sarah Lee | On Track
T004 | Development Phase | 2024-05-16 | 2024-08-31 | 117 | David Kim | Delayed (Review Needed)
T005 | Testing & QA | 2024-09-01 | 2024-10-15 | 66 | Lisa Wong | On Track
T006 | Deployment & Training | 2024-10-16 | 2024-11-30 | 45 | Thomas Reed | In Progress