## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Assigned To
T001 | Project Planning Meeting | 2024-04-01 | 2024-04-01 | 1 | Completed | Jane Doe
T002 | Requirements Gathering | 2024-04-02 | 2024-04-15 | 14 | In Progress | John Smith
T003 | Design Phase Review | 2024-04-16 | 2024-04-18 | 3 | Pending | Lisa Brown
T004 | Development Start | 2024-04-19 | 2024-05-15 | 30 | Not Started | Mike Lee
T005 | Testing & QA Review | 2024-05-16 | 2024-05-31 | 16 | Planned | Sarah Wilson
T006 | Final Deployment | 2024-06-01 | 2024-06-01 | 1 | Not Started | Tom Green