## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Assignee | Progress %
T001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Completed | Alice Johnson | 100%
T002 | Requirements Gathering | 2024-03-16 | 2024-03-25 | 10 | In Progress | Bob Smith | 65%
T003 | Design Phase | 2024-03-26 | 2024-04-15 | 21 | Not Started | Charlie Lee | 0%
T004 | Development Start | 2024-04-16 | 2024-05-31 | 47 | Planned | David Wong | 0%
T005 | Testing & QA | 2024-06-01 | 2024-06-30 | 30 | Not Started | Eva Brown | 0%
T006 | Deployment | 2024-07-01 | 2024-07-15 | 15 | Planned | Frank Miller | 0%