## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status
T001 | Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Alice Johnson | Completed
T002 | Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | Bob Smith | In Progress
T003 | Design Phase | 2024-03-16 | 2024-03-25 | 10 | Cara Lee | Planned
T004 | Development | 2024-03-26 | 2024-04-15 | 21 | Dan Patel | Not Started
T005 | Testing & QA | 2024-04-16 | 2024-04-30 | 15 | Eve Turner | Planned
T006 | Deployment | 2024-05-01 | 2024-05-03 | 5 | Frank Wright | Scheduled