## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assigned To | Priority | Status
T001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | John Doe | High | Completed
T002 | Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Jane Smith | High | In Progress
T003 | Design Phase | 2024-04-11 | 2024-04-25 | 15 | Alex Chen | Medium | Planned
T004 | Development Phase | 2024-04-26 | 2024-05-31 | 36 | Team A | High | Not Started
T005 | Testing & QA | 2024-06-01 | 2024-06-15 | 15 | Lisa Wong | High | Scheduled
T006 | Deployment & Training | 2024-06-16 | 2024-06-30 | 15 | Mike Johnson | Medium | Not Started