## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Assigned To | Status | Progress (%)
T001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Jane Smith | Completed | 100%
T002 | Requirements Gathering | 2024-04-02 | 2024-04-15 | 14 | John Doe | In Progress | 60%
T003 | Design Phase | 2024-04-16 | 2024-05-10 | 35 | Sarah Lee | Not Started | 0%
T004 | Development Phase | 2024-05-11 | 2024-07-31 | 92 | Mike Chen | Not Started | 0%
T005 | Testing & QA | 2024-08-01 | 2024-08-31 | 31 | Lisa Wong | Not Started | 0%
T006 | Final Review & Deployment | 2024-09-01 | 2024-09-15 | 15 | Tom Reed | Not Started | 0%