## Worksheet
Task ID | Task Name | Start Date | End Date
T001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Alice Johnson | High | Completed | None | 100
T002 | Requirements Gathering | 2024-03-16 | 2024-03-31 | 16 | Bob Smith | High | In Progress | T001 | 75
T003 | Design Phase | 2024-04-01 | 2024-04-15 | 15 | Carol Davis | Medium | Not Started | T002 | 0
T004 | Development Phase | 2024-04-16 | 2024-05-31 | 47 | David Lee | High | Not Started | T003 | 0
T005 | Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | Eve Turner | High | Not Started | T004 | 0
T006 | Deployment & Launch | 2024-07-01 | 2024-07-15 | 15 | Frank Wong | Critical | Not Started | T005 | 0