## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible Person
Project Planning | 2024-03-01 | 2024-03-10 | 10 | Completed | Sarah Johnson
Design Phase | 2024-03-11 | 2024-04-05 | 35 | In Progress | Michael Chen
Development Phase | 2024-04-06 | 2024-05-31 | 67 | Not Started | Alex Rivera
Testing & QA | 2024-06-01 | 2024-06-30 | 30 | Not Started | Emily Wong
Final Review & Deployment | 2024-07-01 | 2024-07-15 | 15 | Not Started | David Kim