## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible | Status | Priority | Milestone
T001 | Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | John Smith | On Track | High | Yes
T002 | Market Research & Analysis | 2024-03-16 | 2024-04-05 | 21 | Sarah Lee | On Track | High | Yes
T003 | Product Design & Prototyping | 2024-04-06 | 2024-05-10 | 35 | Mike Chen | On Track | Medium | No
T004 | Development & Coding | 2024-05-11 | 2024-07-30 | 79 | Alex Turner | On Track | High | Yes
T005 | Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | 31 | Linda Patel | On Track | High | Yes
T006 | Deployment & Launch | 2024-09-01 | 2024-09-15 | 15 | David Kim | On Track | Critical | Yes