## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible | Status | Progress (%)
T-001 | Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Manager A | Completed | 100
T-002 | <Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | Team Lead B | In Progress | 65
T-003 | Design Phase | 2024-03-16 | 2024-03-25 | 10 | Designer C | Not Started | 0
T-004 | Development | 2024-03-26 | 2024-04-15 | 20 | Developer D | Planned | 0
T-005 | Testing & QA | 2024-04-16 | 2024-04-30 | 15 | QA Engineer E | Not Started | 0
T-006 | Deployment | 2024-05-01 | 2024-05-03 | 3 | Ops Team | Planned | 0