## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Project Manager | Completed
Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | Business Analyst | In Progress
System Design | 2024-03-16 | 2024-03-25 | 10 | Lead Developer | Not Started
Development Phase | 2024-03-26 | 2024-04-15 | 21 | Development Team | Planned
Testing & QA | 2024-04-16 | 2024-04-30 | 15 | QA Manager | Not Started
Deployment | 2024-05-01 | 2024-05-03 | 3 | Operations Team | Not Started
Post-Deployment Review | 2024-05-04 | 2024-05-06 | 3 | Project Manager | Not Started