## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status
T001 | Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Jane Doe | In Progress
T002 | Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | John Smith | Planned
T003 | Design Phase | 2024-03-16 | 2024-04-05 | 21 | Lisa Chen | Scheduled
T004 | Development Phase | 2024-04-06 | 2024-05-31 | 57 | Mike Johnson | <Not Started
T005 | Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | Sarah Lee | Planned
T006 | Deployment & Launch | 2024-07-01 | 2024-07-15 | 15 | Raj Patel | Finalized