## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Progress (%)
Project Planning | 2024-03-01 | 2024-03-10 | 10 | Sarah Johnson | Completed | 100%
Requirement Gathering | 2024-03-11 | 2024-03-25 | 15 | Michael Chen | In Progress | 60%
System Design | 2024-03-26 | 2024-04-15 | 20 | Lisa Wong | Not Started | 0%
Development Phase | 2024-04-16 | 2024-06-15 | 61 | Team A (Dev) | Not Started | 0%
Testing & Quality Assurance | 2024-06-16 | 2024-07-10 | 35 | James Reed | Not Started | 0%
Deployment & Go-Live | 2024-07-11 | 2024-07-15 | 5 | Alex Torres | Not Started | 0%