## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Planning | 2024-03-15 | 2024-03-18 | 4 | John Doe | Completed
Market Research | 2024-03-19 | 2024-03-25 | 7 | Sarah Lee | In Progress
Design Phase | 2024-03-26 | 2024-04-05 | 10 | Mike Chen | Pending
Development Setup | 2024-04-06 | 2024-04-15 | 10 | Lisa Wong | Not Started
Testing & QA | 2024-04-16 | 2024-04-30 | 15 | David Kim | Scheduled
Final Review & Launch | 2024-05-01 | 2024-05-05 | 5 | Emma Clark | Planned