## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 day | Alice Johnson | Completed
Market Research & Analysis | 2024-03-02 | 2024-03-15 | 14 days | Bob Chen | In Progress
Product Design Phase | 2024-03-16 | 2024-04-10 | 35 days | Carol Smith | Not Started
Development Sprint 1 | 2024-04-11 | 2024-05-05 | 35 days | David Lee | Planned
QA Testing & Bug Resolution | 2024-05-06 | 2024-05-31 | 26 days | Eva Rodriguez | Not Started
Launch Preparation & Training | 2024-06-01 | 2024-06-15 | 15 days | Frank Miller | Not Started