## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Progress (%)
T001 | Project Initiation | 2024-03-15 | 2024-03-18 | 4 | Alice Johnson | Completed | 100
T002 | Requirements Gathering | 2024-03-19 | 2024-03-31 | 13 | Bob Smith | In Progress | 75
T003 | Design Phase | 2024-04-01 | 2024-04-15 | 15 | Carol Lee | Not Started | 0
T004 | Development | 2024-04-16 | 2024-05-31 | 47 | David Kim | Not Started | 0
T005 | Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | Eve Rodriguez | Not Started | 0
T006 | Deployment | 2024-07-01 | 2024-07-15 | 15 | Frank White | Not Started | 0