## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assigned To | Status | Dependencies
T001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Team Lead | Completed | None
T002 | <Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Product Owner | In Progress | T001
T003 | Design Phase | 2024-04-11 | 2024-04-25 | 15 | UI/UX Designer | Planned | T002
T004 | Development Start | 2024-04-26 | 2024-05-15 | 21 | Development Team | Not Started | T003
T005 | Testing Phase | 2024-05-16 | 2024-05-31 | 16 | QA Team | Not Started | T004
T006 | Deployment & Go-Live | 2024-06-01 | 2024-06-05 | 5 | Operations Team | Not Started | T005