## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
T001 | Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Alice Johnson | In Progress | High
T002 | Requirements Gathering | 2024-03-06 | 2024-03-18 | 13 | Bob Smith | Planned | High
T003 | Design Phase | 2024-03-19 | 2024-04-15 | 28 | Charlie Lee | Scheduled | Medium
T004 | Development Phase | 2024-04-16 | 2024-06-30 | 76 | Diana Patel | Planned | High
T005 | Testing & QA | 2024-07-01 | 2024-07-31 | 31 | Evan Brown | Scheduled | Medium
T006 | Deployment & Go-Live | 2024-08-01 | 2024-08-15 | 15 | Fiona Wong | Pending | High