## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assigned To | Status | Progress % | Dependencies
T001 | Project Initiation | 2024-03-01 | 2024-03-15 | 15 | John Doe | Completed | 100% | None
T002 | Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Jane Smith | In Progress | 60% | T001
T003 | Design Phase | 2024-04-11 | 2024-05-15 | 45 | Mike Johnson | Not Started | 0% | T002
T004 | Development Phase | 2024-05-16 | 2024-07-31 | 87 | Sarah Lee | Planned | 0% | T003
T005 | Testing & QA | 2024-08-01 | 2024-09-15 | 60 | David Brown | Not Started | 0% | T004
T006 | Deployment & Launch | 2024-09-16 | 2024-09-30 | 15 | Lisa Wong | Not Started | 0% | T005