## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
TSK-001 | Project Planning Phase | John Doe | 2024-04-01 | 2024-04-15 | 15 | High | Active | None | Initial roadmap and scope definition.
TSK-002 | Requirements Gathering | Sarah Lee | 2024-04-16 | 2024-05-10 | 15 | Medium | In Progress | TSK-001 | Stakeholder interviews and documentation.
TSK-003 | UI/UX Design Review | Mike Chen | 2024-05-11 | 2024-05-25 | 15 | High | Pending Approval | TSK-002 | Design prototypes to be reviewed by PM.
TSK-004 | Development Phase Start | Lisa Wang | 2024-05-26 | 2024-07-31 | 67 | High | Not Started | TSK-003 | Full-stack development begins.
TSK-005 | Testing & QA Cycle | David Park | 2024-08-01 | 2024-08-31 | 31 | Medium | Planned | TSK-004 | Unit and integration testing.
TSK-006 | Deployment & Go-Live | Emma Ross | 2024-09-01 | 2024-09-05 | 5 | High | Not Started | TSK-005 | Production deployment and monitoring.