## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Project Planning Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | 1 | High | Scheduled | None | Review project scope and goals.
T002 | Market Research Phase | John Smith | 2024-04-03 | 2024-04-15 | 13 | Medium | In Progress | T001 | Gather customer feedback and trends.
T003 | UI/UX Design Finalization | Lisa Brown | 2024-04-16 | 2024-04-28 | 13 | High | Scheduled | T002 | Finalize wireframes and prototypes.
T004 | Development Sprint 1 | Mike Taylor | 2024-05-01 | 2024-05-15 | 15 | High | Not Started | T003 | Build core features of the application.
T005 | Testing & QA Review | Sarah Lee | 2024-05-16 | 2024-05-31 | 16 | Medium | Scheduled | T004 | Conduct unit and integration testing.