## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Start Date | Estimated Hours
T001 | Project Kickoff Meeting | John Smith | 2024-04-05 | High | Completed | 2024-04-01 | 2
T002 | Requirement Gathering | Sarah Lee | 2024-04-15 | High | In Progress | 2024-04-03 | 8.5
T003 | Design Finalization | Michael Chen | 2024-04-25 | Medium | Not Started |  | 6
T004 | Development Phase Start | Emily Davis | 2024-05-10 | High | Not Started |  | 24
T005 | Quality Assurance Testing | David Kim | 2024-05-30 | Medium | Not Started |  | 12.5