## Worksheet
Task ID | Task Name | Description | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Progress (%) | Notes
TSK-001 | Project Kickoff Meeting | Organize initial team meeting to define project goals and timelines. | Jane Smith | 2024-04-01 | 2024-04-03 | 3 | High | Completed | None | 100%
TSK-002 | Requirements Gathering | Conduct interviews and workshops to collect detailed user requirements. | Alex Chen | 2024-04-04 | 2024-04-15 | 13 | High | In Progress | TSK-001 | 65% | Need approval from stakeholders.
TSK-003 | Design Phase | Create wireframes and UI mockups for the application. | Maria Garcia | 2024-04-16 | 2024-05-05 | 21 | Medium | Planned | TSK-002 | 0%
TSK-004 | Development Start | Begin coding the core functionality based on approved designs. | David Kim | 2024-05-06 | 2024-06-15 | 41 | High | Not Started | TSK-003 | 0% | Need design finalization.
TSK-005 | Testing & QA | Perform unit, integration, and system testing to ensure quality. | Sarah Lee | 2024-06-16 | 2024-07-10 | 25 | High | Not Started | TSK-004 | 0%
TSK-006 | Go-Live Deployment | Deploy the application to production environment. | John Brown | 2024-07-11 | 2024-07-15 | 5 | Critical | Not Started | TSK-005 | 0%