## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-03 | High | Planned
T002 | Requirements Gathering | Sarah Lee | 2024-04-05 | 2024-04-15 | High | In Progress | Include stakeholder input.
T003 | UI/UX Design Phase | Mike Johnson | 2024-04-16 | 2024-05-10 | Medium | Not Started
T004 | Development Sprint 1 | Team A | 2024-05-11 | 2024-06-05 | High | Planned | Focus on core functionality.
T005 | Testing & QA Phase | Lisa Chen | 2024-06-06 | 2024-07-15 | High | Not Started | Include user acceptance testing.