## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Dependencies | Resources Required | Notes
T001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | High | Pending | None | Meeting Room, Chair, Project Charter | Confirm all stakeholders and distribute project plan.
T002 | Market Research Phase | John Smith | 2024-04-03 | 2024-04-15 | Medium | In Progress | T001 | Survey Tools, Analysts, Data Storage | Collect customer preferences and industry trends.
T003 | Product Design Finalization | Sarah Lee | 2024-04-16 | 2024-05-10 | High | Not Started | T002, T004 | Design Software, UX Team, Feedback Loop | Finalize wireframes and prototypes based on research.
T004 | Development Sprint Planning | Mike Brown | 2024-05-11 | 2024-06-15 | Medium | Not Started | T003 | Dev Team, Version Control, Testing Tools | Set sprint goals and assign tasks to developers.
T005 | Testing & Quality Assurance | Lisa Chen | 2024-06-16 | 2024-07-15 | High | Not Started | T004 | QA Team, Test Environment, Bug Tracker | Validate functionality and fix critical bugs.