## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Deadline Compliance | Notes
TSK-001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-03 | On Track | High | Yes | Initial planning session with stakeholders.
TSK-002 | Design Phase Final Review | Sarah Lee | 2024-04-05 | 2024-04-10 | In Progress | Medium | Pending | Feedback from QA team required.
TSK-003 | Backend Development Start | Mike Johnson | 2024-04-11 | 2024-05-05 | Not Started | High | No | Waiting on database schema approval.
TSK-004 | User Testing Phase | Lisa Wong | 2024-05-15 | 2024-05-30 | Planned | High | Yes | Conduct usability testing with end users.
TSK-005 | Final Report Submission | David Brown | 2024-06-01 | 2024-06-05 | Pending | Low | No | To be finalized after stakeholder review.