## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Notes
T001 | Project Planning Meeting | John Doe | 2024-04-01 | 2024-04-03 | High | Scheduled | Review project goals and timeline with stakeholders.
T002 | Design Phase Initiation | Sarah Lee | 2024-04-05 | 2024-04-15 | Medium | In Progress | Finalize wireframes and user flow diagrams.
T003 | Development Setup | Mike Chen | 2024-04-16 | 2024-04-25 | Low | Pending | Install required tools and configure environments.
T004 | Quality Assurance Review | Lisa Wong | 2024-05-01 | 2024-05-10 | High | Planned | Test all features for bugs and usability.