## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Progress (%)
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | High | Completed | 100%
T002 | Requirements Gathering | Jane Smith | 2024-04-02 | 2024-04-10 | 9 | Medium | In Progress | 60%
T003 | Design Phase Review | Alex Kim | 2024-04-11 | 2024-04-15 | 5 | High | Pending | 0%
T004 | Development Start | Sam Lee | 2024-04-16 | 2024-05-31 | 47 | Medium | Not Started | 0%
T005 | Testing & QA | Taylor Brown | 2024-06-01 | 2024-06-30 | 30 | High | Not Started | 0%