## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Notes
T001 | Project Kickoff Meeting | John Doe | 2023-10-01 | 2023-10-02 | 1 | High | Completed | All stakeholders present and aligned.
T002 | Requirement Gathering | Jane Smith | 2023-10-03 | 2023-10-10 | 7 | Medium | In Progress | Initial sessions with client and users.
T003 | UI/UX Design Phase | Mike Johnson | 2023-10-11 | 2023-10-25 | 14 | High | Planned | Final designs to be reviewed by product lead.
T004 | Development Sprint | Sarah Lee | 2023-10-26 | 2023-11-05 | 10 | High | Scheduled | Frontend and backend implementation.
T005 | Testing & QA Review | David Brown | 2023-11-06 | 2023-11-15 | 9 | Medium | Scheduled | Bug fixes and performance testing.
T006 | Deployment & Go-Live | Lisa Wong | 2023-11-16 | 2023-11-17 | 2 | High | Planned | Live deployment to production environment.