## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Notes
T001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-03 | Completed | Medium | Initial planning session with stakeholders.
T002 | UI/UX Design Finalization | Alex Chen | 2024-04-05 | 2024-04-15 | In Progress | High | Final mockups approved by product team.
T003 | Backend Development Phase | Sam Rivera | 2024-04-16 | 2024-05-10 | Planned | High | API integration and database setup.
T004 | Quality Assurance Testing | Maya Patel | 2024-05-11 | 2024-05-20 | Pending | Medium | Preparation of test cases and bug tracking.