## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Dependence
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | High | Completed
T002 | Requirements Gathering | Lisa Chen | 2024-04-02 | 2024-04-15 | High | In Progress | T001
T003 | UI/UX Design Phase | Mike Torres | 2024-04-16 | 2024-05-10 | Medium | Planned | T002
T004 | Backend Development | Sarah Kim | 2024-05-11 | 2024-06-30 | High | Not Started | T003
T005 | Testing & QA Review | David Brown | 2024-07-01 | 2024-07-15 | Medium | Planned | T004