## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Notes
T001 | Project Kickoff Meeting | Sarah Chen | 2024-04-01 | 2024-04-03 | High | Planned | Review project scope and team roles.
T002 | UI/UX Design Phase | James Park | 2024-04-05 | 2024-04-18 | High | In Progress | Finalize wireframes and user flows.
T003 | Backend Development | Lena Torres | 2024-04-19 | 2024-05-15 | Medium | Not Started | Develop APIs and database schema.
T004 | QA Testing | Mike Wu | 2024-05-16 | 2024-05-30 | Medium | Planned | Conduct end-to-end testing cycles.
T005 | Deployment & Launch | Team Lead | 2024-06-01 | 2024-06-05 | High | Not Started | Deploy to production environment.