## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Duration (Days)
T001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | Completed | Medium | 1
T002 | Requirements Gathering | John Smith | 2024-04-02 | 2024-04-15 | In Progress | High | 14
T003 | Design Phase Review | Alice Brown | 2024-04-16 | 2024-04-20 | Planned | Medium | 5
T004 | Development Sprint 1 | Team A | 2024-04-21 | 2024-05-05 | Not Started | High | 15
T005 | Testing & QA Validation | Mike Lee | 2024-05-06 | 2024-05-31 | Planned | High | 26