## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Notes
T001 | Project Planning Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | High | Pending | Confirm stakeholders and deliverables.
T002 | Design Phase Completion | Mike Johnson | 2024-04-05 | 2024-04-15 | Medium | In Progress | Finalize UI mockups and present to client.
T003 | Development Sprint | Sarah Lee | 2024-04-16 | 2024-04-30 | High | Planned | Implement core features according to sprint plan.
T004 | Quality Assurance Review | David Kim | 2024-05-01 | 2024-05-10 | Medium | Not Started | Test all modules for bugs and performance.